## Sheet1
Task | Deadline
1 Mechanics
1.1 Create prototype fiberglass shell | 2016-10-16
1.2 Run durability tests on fiberglass shell | 2016-10-20
1.3 Create final fiberglass shell | 2017-05-15
1.4 Machine final fiberglass shell | 2017-05-18
1.5 Create CAD models of sensors, development boards, and radios | 2017-05-01
1.6 Brainstorm internal CanSat layout | 2017-03-01
1.7 Create CAD model of internal CanSat layout | 2017-04-01
1.8 Create CAD model of internal frame and sliders | 2017-04-01
1.9 Brainstorm manufacturing options for internal frame | 2017-04-05
1.10 Manufacture internal supports / frame from CAD | 2017-05-01
1.11 Assemble mechanical portion of CanSat | 2017-06-01
2 Electronics
2.1 Decide on final capability list | 2016-10-01
2.2 Select sensors, MCU, and radio to fulfill final capability list | 2016-11-01
2.3 Select required battery size and technology to support sensors and MCU | 2016-11-06
2.4 Order sensors, MCU, radio, and battery | 2016-11-10
2.5 Test system on a breadboard | 2016-12-01
2.6 Design PCB layouts for internal electronics | 2016-05-01
2.7 Order PCBs | 2016-05-03
2.8 Assemble electronics portion of CanSat | 2016-06-01
2.9 Conduct radio tests with MCU and PC | 2016-06-10
2.10 Test radio range between MCU and PC | 2016-06-10
3 Software
3.1 Create basic “hello world” program for MCU | 2016-12-01
3.2 Create basic sensor tests for MCU | 2016-12-15
3.3 Create graphing and IO system for PC | 2017-02-01
3.4 Implement two way communication capability between PC and CanSat | 2017-03-01
3.5 Create unified data logging and and telemetry system and API for CanSat | 2017-05-01
3.6 Create final PC program incorporating all tested features | 2017-06-01
4 Parachute
4.1 Brainstorm and prototype initial parachute designs | 2016-11-01
4.2 Test prototype parachute designs | 2016-12-01
4.3 Create and test final parachute | 2016-01-01
Advertisement and Sponsorship
5.1 Discuss sponsorship options with school | 2016-10-01
5.2 Discuss sponsorship options with interested companies | 2016-12-01
5.3 Acquire 2000 GBP total in funding | 2016-03-01
5.4 Create advertising materials for school Open Day | 2016-11-23
5.5 Create presentation for school assembly | 2017-03-18
5.6 Decide on activities for P5 workshop | 2017-04-09
5.7 Collect materials and design experiment for P5 workshop | 2017-04-18
5.8 Participate in Edinburgh Maker Faire | 2017-04-16
5.9 Create materials for Edinburgh Maker Faire | 2017-04-12
5.10 Set up social media accounts | 2016-10-01
5.11 Create temporary website | 2016-10-01
5.12 Create permanent website | 2016-01-01
5.13 Migrate materials to permanent website | 2016-01-05